## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ashok | 2024-12-15 | User registration fails when entering an invalid email address. | 1 | Ashok | Logical | Corrected validation logic for email addresses. | 2024-12-16 | Closed | NA
2 | Prashant | 2024-12-18 | The "Forgot Password" link is not displayed correctly on the login page. | 1 | Prashant | User Interface | Fixed the display issue and updated CSS. | 2024-12-19 | Closed | NA
3 | Krishna Karthik | 2024-12-21 | The user management module lacks proper comments and documentation. | 1 | Krishna Karthik | Maintainability | Added detailed comments and documentation to the code | 2024-12-23 | Closed | Improved code readability and maintainability.
4 | Ashok | 2024-12-27 | The restaurant name field in the restaurant profile creation form is too short. | 2 | Ashok | User Interface | ncreased the character limit for the restaurant name field. | 2024-12-30 | Closed | NA
5 | Rohit | 2025-01-02 | The system fails to handle orders with more than 10 items. | 3 | Rohit | Logical | Fixed the order processing logic to handle larger orders. | 2025-01-04 | Closed | NA
6 | Prashant | 2025-01-08 | The menu management code lacks proper error handling. | 3 | Prashant | Maintainability | Implemented robust error handling and logging for menu management operations. | 2025-01-10 | Closed | Improved system stability and maintainability.
7 | Santhosh | 2025-01-15 | The order confirmation email does not include the restaurant name. | 3 | Krishna Karthik | Standards | Updated the email template to include the restaurant name. | 2025-01-16 | Closed | Improved email clarity and user experience.
8 | Ashok | 2025-01-17 | The system crashes when attempting to place an order for a non-existent menu item. | 3 | Santhosh | Logical | Added validation checks to prevent orders for non-existent items. | 2025-01-18 | Closed | Improved system stability and user experience.
9 | Ashok | 2025-01-22 | Feedback form submission fails when entering special characters in the feedback message. | 4 | Ashok | Logical | Added input validation and sanitization for special characters. | 2025-01-23 | Closed | NA
10 | Krishna Karthik | 2025-01-24 | The "Feedback Type" dropdown menu is not displaying correctly on some browsers. | 4 | Krishna Karthik | User Interface | Updated CSS and JavaScript for better compatibility across browsers. | 2025-01-25 | Closed | NA
11 | Prashant | 2025-01-27 | Report generation for large date ranges is slow. | 4 | Prashant | Standards | Optimized the report generation queries and added caching mechanisms. | 2025-01-26 | Closed | Improved report loading time significantly.
12 | Rohit | 2025-01-28 | The "Export to PDF" functionality for reports is not working correctly. | 4 | Rohit | Maintainability | Fixed the PDF export functionality and added error handling. | 2025-01-29 | Closed | NA
13 | Santhosh | 2025-01-30 | The feedback form does not have a "Severity" field for users to indicate the urgency of the issue. | 4 | Santhosh | Maintainability | Added a "Severity" field to the feedback form (e.g., Low, Medium, High). | 2025-01-31 | Closed | Improved feedback prioritization.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others